## Slide 1: Budget
Cost Estimating
Estimate each individual task based on market price and relational documents
2. Cost Budgeting
Determine the cost baseline
3. Cost Controlling
Determine the cost control baseline

## Slide 2: Budget
Cost Estimating
Chart: 
| Project Management | Hardware | Software | Research & Development | Test | Training and Support | Commercial | Reserves
 | 0.036076 | 0.14586 | 0.016064 | 0.369 | 0.12 | 0.03 | 0.083 | 0.2

## Slide 3: Budget
Cost Budgeting
Year/Resource Name | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 8.08
Project Management | 282691 | 282691 | 282691 | 282691 | 282691 | 282691 | 282691 | 282691 | 22615.28
Hardware | 418630.6657 | 362650.6657 | 362650.6657 | 362650.6657 | 362650.6657 | 362650.6657 | 362650.6657 | 362650.6657 | 29012.05326
Software | 175103.7534 | 123011 | 123011 | 123011 | 123011 | 123011 | 123011 | 123011 | 9840.88
Research & Development | 11532291.17 | 1764899.907 | 1764899.907 | 1764899.907 | 1764899.907 | 1764899.907 | 1764899.907 | 1764899.907 | 141191.9925
Test | - | 1302318.835 | 1302318.835 | 1953478.253 | 1085265.696 | 1085265.696 | 1085265.696 | - | -
Training and Support | 241767.1105 | 241767.1105 | 241767.1105 | 241767.1105 | 241767.1105 | 241767.1105 | 241767.1105 | 241767.1105 | 19341.36884
Commercial | - | - | - | - | - | - | - | 5404623.166 | -
Reserves | 1611780.737 | 1611780.737 | 1611780.737 | 1611780.737 | 1611780.737 | 1611780.737 | 1611780.737 | 1611780.737 | 1611780.737
Total | 14262264.44 | 5689119.255 | 5689119.255 | 6340278.672 | 5472066.115 | 5472066.115 | 5472066.115 | 9791423.586 | 1833782.311

## Slide 4: Budget
Cost Controlling
Tracked Monthly
Actual Cost
Schedule of each task
Calculated Monthly
Earned Value
Planned Value
Budget at Completion
Estimate at Completion
Earned Value Chart
Decision
Budget Changing
Cost Estimating Update
Cost Baseline Update