## Slide 1
Budget
1. Cost Estimating
2. Cost Budgeting
3. Cost Controlling

## Slide 2
1. Cost Estimating
ID | Resource Name | Type | Material Label | Units | Time(year) | Cost per year(AU$) | Subtotals | % of Total
1 | Project Management |  |  |  |  |  | 2,349,143.28 | 3.61%
 | Project Manager, Information Technology | Labor | Person | 1 | 8.08 | 100,812.00 | 814,560.96 | 1.25%
 | Research & Development (R&D) Manager | Labor | Person | 1 | 8.08 | 83,849.00 | 677,499.92 | 1.04%
 | Information Technology (IT) Manager | Labor | Person | 1 | 8.08 | 98,030.00 | 792,082.40 | 1.22%
 | Market Manager | Labor | Person | 1 | 1 | 65,000.00 | 65,000.00 | 0.10%
2 | Hardware |  |  |  |  |  | 9,497,791.56 | 14.59%
 | Computer | Equipment | Unit | 20 |  |  | 55,980.00 | 0.09%
 | Laboratory | Building | Unit | 1 | 8.08 | 161,178.07 | 1,302,318.84 | 2.00%
 | Research Equipment | Equipment |  |  |  |  | 6,511,594.18 | 10.00%
 | Research Office | Building | Unit | 1 | 8.08 | 120,883.56 | 976,739.13 | 1.50%
 | General Business Office | Building | Unit | 1 | 8.08 | 80,589.04 | 651,159.42 | 1.00%

## Slide 3
1. Cost Estimating
3 | Software |  |  |  |  |  | 1,046,021.63 | 1.61%
 | Licensed Software | Equipment | Unit | 5 |  |  | 52,092.75 | 0.08%
 | Software Engineer / Developer / Programmer | Labor | person | 2 | 8.08 | 68,897.00 | 556,687.76 | 0.85%
 | Computer Aided Design (CAD) Drafter | Labor | person | 1 | 8.08 | 54,114.00 | 437,241.12 | 0.67%
4 | Research & Development |  |  |  |  |  | 24,027,782.51 | 36.90%
 | Physician / Doctor, Cardiologist | Labor | person | 6 | 8.08 | 1,611,780.74 | 13,023,188.35 | 20.00%
 | Printer Development | Labor | person | 2 | 0.5 |  | 9,767,391.26 | 15.00%
 | Consume | Material |  |  | 8.08 | 153,119.17 | 1,237,202.89 | 1.90%
5 | Test |  |  |  |  |  | 7,813,913.01 | 12.00%
 | Lab Test |  |  |  | 2 | 1,302,318.84 | 2,604,637.67 | 4.00%
 | Functional Test |  |  |  | 1 |  | 1,953,478.25 | 3.00%
 | Clinical Trial |  |  |  | 3 | 1,085,265.70 | 3,255,797.09 | 5.00%

## Slide 4
1. Cost Estimating
6 | Training and Support |  |  |  |  |  | 1,953,478.25 | 3.00%
 | Trainee Cost |  |  |  | 8.08 | 161,178.07 | 1,302,318.84 | 2.00%
 | Travel Cost |  |  | 16 | 8.08 | 80,589.04 | 651,159.42 | 1.00%
7 | Commercial |  |  |  |  |  | 5,404,623.17 | 8.30%
 | Customer Service Officer | Labor | person | 1 | 1 |  | 39,069.57 | 0.06%
 | Marketing Specialist | Labor | person | 1 | 1 |  | 26,046.38 | 0.04%
 | Advertisement |  |  |  |  |  | 5,144,159.40 | 7.90%
 | Consume | Material |  |  |  |  | 195,347.83 | 0.30%
8 | Reserves |  |  |  |  |  | 13,023,188.35 | 20.00%

## Slide 5
2. Cost Budgeting
Cost Baseline
Resource Name | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 8.08 | Totals
Project Management |  |  |  |  |  |  |  |  |  | 2,349,143.28
Project Manager, Information Technology | 100,812.00 | 100,812.00 | 100,812.00 | 100,812.00 | 100,812.00 | 100,812.00 | 100,812.00 | 100,812.00 | 8064.96 | 814,560.96
Research & Development (R&D) Manager | 83,849.00 | 83,849.00 | 83,849.00 | 83,849.00 | 83,849.00 | 83,849.00 | 83,849.00 | 83,849.00 | 6707.92 | 677,499.92
Information Technology (IT) Manager | 98,030.00 | 98,030.00 | 98,030.00 | 98,030.00 | 98,030.00 | 98,030.00 | 98,030.00 | 98,030.00 | 7842.4 | 792,082.40
Market Manager |  |  |  |  |  |  |  | 65,000.00 |  | 65,000.00
Hardware |  |  |  |  |  |  |  |  |  | 9,497,791.56
Computer | 55,980.00 |  |  |  |  |  |  |  |  | 55,980.00
Laboratory | 161,178.07 | 161,178.07 | 161,178.07 | 161,178.07 | 161,178.07 | 161,178.07 | 161,178.07 | 161,178.07 | 12894.246 | 1,302,318.84
Research Equipment |  |  |  |  |  |  |  |  |  | 6,511,594.18
Research Office | 120,883.56 | 120,883.56 | 120,883.56 | 120,883.56 | 120,883.56 | 120,883.56 | 120,883.56 | 120,883.56 | 9670.6844 | 976,739.13
General Business Office | 80,589.04 | 80,589.04 | 80,589.04 | 80,589.04 | 80,589.04 | 80,589.04 | 80,589.04 | 80,589.04 | 6447.1229 | 651,159.42

## Slide 6
Cost Baseline
Resource Name | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 8.08 | Totals
Software |  |  |  |  |  |  |  |  |  | 1,046,021.63
Licensed Software | 52,092.75 |  |  |  |  |  |  |  |  | 52,092.75
Software Engineer / Developer / Programmer | 68,897.00 | 68,897.00 | 68,897.00 | 68,897.00 | 68,897.00 | 68,897.00 | 68,897.00 | 68,897.00 | 5511.76 | 556,687.76
Computer Aided Design (CAD) Drafter | 54,114.00 | 54,114.00 | 54,114.00 | 54,114.00 | 54,114.00 | 54,114.00 | 54,114.00 | 54,114.00 | 4329.12 | 437,241.12
Research & Development |  |  |  |  |  |  |  |  |  | 24,027,782.51
Physician / Doctor, Cardiologist | 1,611,780.74 | 1,611,780.74 | 1,611,780.74 | 1,611,780.74 | 1,611,780.74 | 1,611,780.74 | 1,611,780.74 | 1,611,780.74 | 128942.5 | 13,023,188.35
Printer Development | 9,767,391.26 |  |  |  |  |  |  |  |  | 9,767,391.26
Consume | 153,119.17 | 153,119.17 | 153,119.17 | 153,119.17 | 153,119.17 | 153,119.17 | 153,119.17 | 153,119.17 | 12249.53 | 1,237,202.89
Test |  |  |  |  |  |  |  |  |  | 7,813,913.01
Lab Test |  | 1,302,318.84 | 1,302,318.84 |  |  |  |  |  |  | 2,604,637.67
Functional Test |  |  |  | 1,953,478.25 |  |  |  |  |  | 1,953,478.25
Clinical Trial |  |  |  |  | 1,085,265.70 | 1,085,265.70 | 1,085,265.70 |  |  | 3,255,797.09

## Slide 7
Cost Baseline
Resource Name | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 8.08 | Totals
Training and Support |  |  |  |  |  |  |  |  |  | 1,953,478.25
Trainee Cost | 161,178.07 | 161,178.07 | 161,178.07 | 161,178.07 | 161,178.07 | 161,178.07 | 161,178.07 | 161,178.07 | 12894.25 | 1,302,318.84
Travel Cost | 80,589.04 | 80,589.04 | 80,589.04 | 80,589.04 | 80,589.04 | 80,589.04 | 80,589.04 | 80,589.04 | 6447.123 | 651,159.42
Commercial |  |  |  |  |  |  |  |  |  | 5,404,623.17
Customer Service Officer |  |  |  |  |  |  |  | 39,069.57 |  | 39,069.57
Marketing Specialist |  |  |  |  |  |  |  | 26,046.38 |  | 26,046.38
Advertisement |  |  |  |  |  |  |  | 5,144,159.40 |  | 5,144,159.40
Consume |  |  |  |  |  |  |  | 195,347.83 |  | 195,347.83
Reserves |  |  |  |  |  |  |  |  |  | 13,023,188.35

## Slide 8
3. Cost Controlling
The actual cost and the schedule of the task tracked by the project manager monthly
Earned Value
Planned Value
Budget at Completion
Estimate at Completion
Earned Value Chart
All of the stakeholders and the project manager make the decision on changing the budget